## Sheet1
|  |  | Smart PM Maintenance | [6 empty] | Preventive Maintenance System
Total Machines | Planned Tasks | Done Tasks | Remaining | Achievement % | Calendar Tasks | Hours Tasks | PLC Tasks |  | W1 Plan | W1 Done | W1 % | W2 Plan | W2 Done | W2 % | W3 Plan | W3 Done | W3 % | W4 Plan | W4 Done | W4 % | W5 Plan | W5 Done | W5 % | Month
Preparation — Aug 2026
[15 empty] | PM WEEK SCHEDULE |  |  |  |  | Executed By / Execution Date
[15 empty] | 7--13 | 14--20 | 21--27 | 28--3 |  | 7--13 | 14--20 | 21--27 | 28--3
Section | Machine No. | Machine Name | Machine Identified | Manufacturer | Part | Maintenance | Row Type | PM Code | Frequency Value | Freq. | Calculation Mode | PLC Tag / Counter | First PM Date | Notes | W1 | W2 | W3 | W4 | W5 | Audit W1 | Audit W2 | Audit W3 | Audit W4 | Audit W5
Preparation | P01 | Microwave | P01 Microwave | Amtek | Heat exchanger & Recervoir | Check the water level in the heat exchanger reservoir & check the strainer filter for the same reservoir | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | Admin |  |  |  |  | P01 | 161883bb-4935-4a8c-8df5-dfeb914eb5ff
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P01 | 161883bb-4935-4a8c-8df5-dfeb914eb5ff
[5 empty] | Water System | Check for any water leaks | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P01 | 2bab601b-356e-4faa-8ee2-9b49daf2d14b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 2bab601b-356e-4faa-8ee2-9b49daf2d14b
[5 empty] | Transmitter | Inspect the capacitors on solenoid protect board in the transmitter | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P01 | 14b996d3-bc5a-4282-ae07-2052a9cbb032
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 14b996d3-bc5a-4282-ae07-2052a9cbb032
[5 empty] | Transmitter | Check the transmitter doors and waveguide connections for R.F Leakage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P01 | afcef142-f510-4d68-82ca-4ac6f8eca610
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | afcef142-f510-4d68-82ca-4ac6f8eca610
[5 empty] | Door | Inspect the shunt trip breakers (door safety) | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | Admin |  |  |  |  | P01 | b4fe6478-e227-4987-920a-261756b415e6
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P01 | b4fe6478-e227-4987-920a-261756b415e6
[5 empty] | Door | Tighten and secure the main breakers wire connections and the high voltage transformer connections | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P01 | 78b6b612-0310-45c2-b2cf-8676d86fd133
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 78b6b612-0310-45c2-b2cf-8676d86fd133
[5 empty] | High Voltage Wire | Check the high voltage wire jumper condition | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P01 | 41b9a19a-7354-4a00-9be9-91b952d6e186
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 41b9a19a-7354-4a00-9be9-91b952d6e186
[5 empty] | Filament | Check standby filament calibration | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P01 | dcc308b8-c3cf-48cc-ac45-938f58e727c7
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | dcc308b8-c3cf-48cc-ac45-938f58e727c7
[5 empty] | Fans | Check the fans operaion | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | Admin |  |  |  |  | P01 | b492bc46-58c3-40a8-a33f-92ca184e55bb
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P01 | b492bc46-58c3-40a8-a33f-92ca184e55bb
[5 empty] | Contactor | Remove face K1 contactor and inspect the contacts | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P01 | d72f8f88-0d10-4ab4-99b3-47c906c55cfd
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | d72f8f88-0d10-4ab4-99b3-47c906c55cfd
[5 empty] | Oven Chamber | Check the oven chamber for cleanliness | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P01 | 83b99a2b-93bb-4ad6-a652-62aa89f26776
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 83b99a2b-93bb-4ad6-a652-62aa89f26776
[5 empty] | Doors | Check the doors for any damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P01 | 5d2ab813-bb3d-4ee2-b864-054769e107aa
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 5d2ab813-bb3d-4ee2-b864-054769e107aa
[5 empty] | Antenna | Check the antenna flanges and covers for damage or burn marks | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | Admin |  |  |  |  | P01 | c1b21507-9b70-4c08-a286-f54250242de5
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P01 | c1b21507-9b70-4c08-a286-f54250242de5
[5 empty] | Leakage System | Perform leakage check on system | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P01 | 4503f823-c064-46fb-a768-1901549b1433
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 4503f823-c064-46fb-a768-1901549b1433
[5 empty] | Gear Boxes | Check the motors gearboxes for oil leakage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P01 | 25b07a28-b612-4b31-83fe-6fa764cc514a
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | 25b07a28-b612-4b31-83fe-6fa764cc514a
[5 empty] | Conveyor Bearing | Grease the conveyor shaft bearings | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P01 | ab353118-c029-4ac4-b4fa-df3dec5041cc
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P01 | ab353118-c029-4ac4-b4fa-df3dec5041cc
| P02 | Elevator | P02 Elevator | Bonner | Electric Part | Check all electric Parts functionality | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | Admin |  |  |  |  | P02 | 8dec5a64-3c70-41c7-ad3a-b8355eaebfd4
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P02 | 8dec5a64-3c70-41c7-ad3a-b8355eaebfd4
[5 empty] | Bearing | Grease all Bearing | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | Admin |  |  |  |  | P02 | 0b047c29-39dd-4d3f-85b0-50f0de0e9603
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P02 | 0b047c29-39dd-4d3f-85b0-50f0de0e9603
[5 empty] | Chain | Lubrication of Chain, Sliding tube | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | Admin |  |  |  |  | P02 | bafdc641-b0b7-47ce-bae5-a49613f7edba
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P02 | bafdc641-b0b7-47ce-bae5-a49613f7edba
[5 empty] | Chain | Check Self locking, | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | Admin |  |  |  |  | P02 | 59928304-db08-4ed2-a37e-cd0857eef8a2
[7 empty] | done | [7 empty] | 6 | 0 | 0 | 0 | 0 | 2026-08-12 09:00 |  |  |  |  | P02 | 59928304-db08-4ed2-a37e-cd0857eef8a2
[5 empty] | Chain | Visual Powe Cable & Electric capinet & Seal | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P02 | 5ac8f394-08fd-4417-95b7-b683b0fd9622
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | 5ac8f394-08fd-4417-95b7-b683b0fd9622
[5 empty] | Chain | check oil level in the gearbox. | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P02 | 93805ebd-367c-4c9c-9d43-9560f223b3c5
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | 93805ebd-367c-4c9c-9d43-9560f223b3c5
[5 empty] | Chain | Check all screws connectiom | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P02 | c98e1301-cf9f-4a73-9c93-86da12471a28
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | c98e1301-cf9f-4a73-9c93-86da12471a28
[5 empty] | Chain | Chain Stretched | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | f349beb7-b2d3-47ad-b369-9ddff331162f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | f349beb7-b2d3-47ad-b369-9ddff331162f
[5 empty] | Chain | change the gearbox oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | a4905155-1bb7-42c1-ac6a-b25c58a33f15
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | a4905155-1bb7-42c1-ac6a-b25c58a33f15
[5 empty] | Chain | Check Gearbox brek, Bushing ,fork & Sprocket | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | 5ce6d390-0c8f-4c80-8b80-c5b3f41553fc
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P02 | 5ce6d390-0c8f-4c80-8b80-c5b3f41553fc
| P03 | Belt Loader | P03 Belt Loader | Helligns | Bearing | Grease the bearing, linear guidance & Roller chain | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P03 | fb03d14d-6614-4c4e-9ee4-5ecb4c8907ac
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | fb03d14d-6614-4c4e-9ee4-5ecb4c8907ac
[5 empty] | Gear Box | check the gearbox oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 95670e00-1092-4a28-a19a-420e20d2bd36
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 95670e00-1092-4a28-a19a-420e20d2bd36
[5 empty] | Gear Box | Check Damage or crosiom , fracture , cracking, wear &tear | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P03 | 52eb84e9-03d3-4556-95b1-d485768bbb6c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 52eb84e9-03d3-4556-95b1-d485768bbb6c
[5 empty] | Gear Box | Check Fastnes are secure & Bearing Condition | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 22ab2438-6825-494f-bc77-9dec3156b727
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 22ab2438-6825-494f-bc77-9dec3156b727
[5 empty] | Gear Box | Check cracking of the control cabinet | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 3 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 2e876200-179f-4f74-8aae-833e818c0833
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 2e876200-179f-4f74-8aae-833e818c0833
[5 empty] | Gear Box | Check cables and no musture around electric parts | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 43871d9e-5598-4410-83e4-73b715c4d410
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 43871d9e-5598-4410-83e4-73b715c4d410
[5 empty] | Gear Box | Inspect Belt Material,sprocket,returnblock,strips,connection wear & tear | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 530ccbcd-e933-4fd4-b304-743359cd0b5f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P03 | 530ccbcd-e933-4fd4-b304-743359cd0b5f
| P04 | X-Ray | P04 X-Ray | Marel |  | Check Electric Parts & alarm | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P04 | 01a0a873-2da9-4a6c-9eac-2d0ffe033ec6
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P04 | 01a0a873-2da9-4a6c-9eac-2d0ffe033ec6
[6 empty] | Cheeck Belt Condition | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P04 | 9f2ff151-bcb7-419a-8fa0-ab6668cf4c6d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P04 | 9f2ff151-bcb7-419a-8fa0-ab6668cf4c6d
| P05 | DSI 01 | P05 DSI 01 | Marel | Rollers | For infeed belt Inspect the carrier rollers, make sure they roll freely | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 5202545e-05a9-494b-b9f3-93456c9f9a97
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 5202545e-05a9-494b-b9f3-93456c9f9a97
[5 empty] | Laser Mounting | Adjust loading laser mounting blocks | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | a9e5feef-fe02-4860-a732-c37baa411e14
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | a9e5feef-fe02-4860-a732-c37baa411e14
[5 empty] | Laser Strips | Inspect he laser strips, make sure they are straight and aligned | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 7912920c-7d99-402b-a1ed-98712fcf3876
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 7912920c-7d99-402b-a1ed-98712fcf3876
[5 empty] | Transfer Gaps | For infeed belt,Make sure that transfer gap is 1/8" | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 80d66561-66ac-4baa-b1c6-ffb62a759fca
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 80d66561-66ac-4baa-b1c6-ffb62a759fca
[5 empty] | Outfeed Belt | For outfeed belt, inspect spray nozzles, make sure they areon and aligned | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 54f64359-81c7-4d03-aa52-a0ec5e08b7e1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 54f64359-81c7-4d03-aa52-a0ec5e08b7e1
[5 empty] | Outfeed Belt | Inspect the condition of outfeed belt, check for any wear | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | d3d59209-1de3-4bcf-a1b4-0f2ccc6d848a
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | d3d59209-1de3-4bcf-a1b4-0f2ccc6d848a
[5 empty] | Bearing | Inspect the the outfeed bearings for any overheat or damage | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | aa60d4e4-b843-43b0-ba39-fdd4fada5b73
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | aa60d4e4-b843-43b0-ba39-fdd4fada5b73
[5 empty] | Sprocket | Inspect the condition of sprockets | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 4ac8307f-fc88-45de-966a-536b53cfe726
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 4ac8307f-fc88-45de-966a-536b53cfe726
[5 empty] | Scan & Cut Assembly | Inspect the camera window,clean if necessary , Loose Mounting, Bearing , carige tracks (x-Axis)& Y axis,Belts, Guid strips , evacuation Fan, Pullys,orifice Strem, Electrictower | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 427a24a3-d6af-4dfb-9cf1-79d94b318951
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 427a24a3-d6af-4dfb-9cf1-79d94b318951
[5 empty] | Laser Alignment | Inspect the scan laser alignment, should be sharp and perpendicular to infeed belt | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 71c4619f-42e9-4021-8890-7467df9ee936
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 71c4619f-42e9-4021-8890-7467df9ee936
[5 empty] | Air Dryer | Check Air dryer working and mustire of servo | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P05 | d889c990-d357-4c98-93e9-d980d8219f24
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | d889c990-d357-4c98-93e9-d980d8219f24
[5 empty] | Misclinious | Check and replace if needed Scan Envclosure, Dervo Mpotor enclosure , Electric Elclosure | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 2dcf2957-e33d-4a6f-bc6f-82cf42e537b0
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 2dcf2957-e33d-4a6f-bc6f-82cf42e537b0
[5 empty] | Rollers | For infeed belt Inspect the carrier rollers, make sure they roll freely | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | e0c8e3f6-7ea7-409a-861d-f32ca6ac2346
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | e0c8e3f6-7ea7-409a-861d-f32ca6ac2346
[5 empty] | Laser Mounting | Adjust loading laser mounting blocks | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 806cc3a0-c3ff-44c9-8371-b7811de3b94c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 806cc3a0-c3ff-44c9-8371-b7811de3b94c
[5 empty] | Laser Strips | Inspect he laser strips, make sure they are straight and aligned | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 2a01e68d-159d-496e-9115-1a0a0cde55b2
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 2a01e68d-159d-496e-9115-1a0a0cde55b2
[5 empty] | Transfer Gaps | For infeed belt,Make sure that transfer gap is 1/8" | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | a7ee0e55-74af-4a4d-8dca-4efe05dbe1e6
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | a7ee0e55-74af-4a4d-8dca-4efe05dbe1e6
[5 empty] | Outfeed Belt | For outfeed belt, inspect spray nozzles, make sure they areon and aligned | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 0c1b8052-6787-4d2e-8beb-b2ecd73c433d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 0c1b8052-6787-4d2e-8beb-b2ecd73c433d
[5 empty] | Outfeed Belt | Inspect the condition of outfeed belt, check for any wear | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | a86ec439-aac8-4c5c-a4aa-040f0e503f37
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | a86ec439-aac8-4c5c-a4aa-040f0e503f37
[5 empty] | Bearing | Inspect the the outfeed bearings for any overheat or damage | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 9e66e95e-f095-45d7-b44e-9b04809ddde1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 9e66e95e-f095-45d7-b44e-9b04809ddde1
[5 empty] | Sprocket | Inspect the condition of sprockets | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | b3d52a48-7c36-4b9e-99d6-8de831a7ed9e
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | b3d52a48-7c36-4b9e-99d6-8de831a7ed9e
[5 empty] | Scan & Cut Assembly | Inspect the camera window,clean if necessary , Loose Mounting, Bearing , carige tracks (x-Axis)& Y axis,Belts, Guid strips , evacuation Fan, Pullys,orifice Strem, Electrictower | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 6f884d13-962f-4d44-aa6c-7f4828851837
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 6f884d13-962f-4d44-aa6c-7f4828851837
[5 empty] | Laser Alignment | Inspect the scan laser alignment, should be sharp and perpendicular to infeed belt | planed | 1 | 1 | Weekly | Calendar |  |  |  | 1 | 1 | 1 | 1 | 0 | [5 empty] | P05 | 9765865b-6d15-4a4f-9bc4-93f161865bac
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 9765865b-6d15-4a4f-9bc4-93f161865bac
[5 empty] | Air Dryer | Check Air dryer working and mustire of servo | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P05 | 0a9bf812-2bbe-46e9-83e2-fdb330a63ecd
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 0a9bf812-2bbe-46e9-83e2-fdb330a63ecd
[5 empty] | Misclinious | Check and replace if needed Scan Envclosure, Dervo Mpotor enclosure , Electric Elclosure | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 2a81d295-f173-4491-b66f-d34a82483f6f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P05 | 2a81d295-f173-4491-b66f-d34a82483f6f
| P06 | Grinder | P06 Grinder | Marel | Worm | Inspect feeder worm and meat worm drive motors | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 1656a8e3-abe6-4afa-ac7c-6c157b06dfd8
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 1656a8e3-abe6-4afa-ac7c-6c157b06dfd8
[5 empty] | Gear Box | Inspect the oil level, temperature of Gearboxes | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P06 | 759ea8f0-03f4-4bd8-ad12-b4f721ca1855
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 759ea8f0-03f4-4bd8-ad12-b4f721ca1855
[5 empty] | Conveyors | Inspect the drive belts condition and tension, adjust tension if necessary | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P06 | 2ce94540-a551-43ff-b202-6136c191bc5f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 2ce94540-a551-43ff-b202-6136c191bc5f
[5 empty] | Housing | Clean the machine housing and wash the worms seals through the existing water inlets | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P06 | 40afe077-674a-43a0-89ce-1b310e2a37d3
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 40afe077-674a-43a0-89ce-1b310e2a37d3
[5 empty] | Electric Panel | Clean and isnpect the electrical control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 6be583c0-8c06-464b-9510-4cdd889c5514
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 6be583c0-8c06-464b-9510-4cdd889c5514
[5 empty] | Safety Sensor | Activate and test all safety sensors for poper operation | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P06 | b5e3a3e6-0fd0-4681-9112-ec7c718b28e6
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | b5e3a3e6-0fd0-4681-9112-ec7c718b28e6
[5 empty] | Worm Bushing | Inspect meat worm bushing, replace if it is loose and worn out | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | d2b92f57-19f8-4f7b-a0a3-e1ab69aecc21
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | d2b92f57-19f8-4f7b-a0a3-e1ab69aecc21
[5 empty] | Plates | Inspect precutter & hole plates (original thickness 22 mm), and blade for any wear or crack, maximum thickness reduction should not be more than 5 mm, make surfacing if necessary | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 3 | 0 | 0 | 0 | [5 empty] | P06 | 191f06e9-860f-4afb-8734-6544bcc12176
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 191f06e9-860f-4afb-8734-6544bcc12176
[5 empty] | Electric Cabel | Inspect power supply cable and other cables condition | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 4 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 03fd5a36-cb6a-4bf5-8f89-aae5980c614c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 03fd5a36-cb6a-4bf5-8f89-aae5980c614c
[5 empty] | Doors | Inspect all doors rubber seal | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 30a03d47-507d-4ad6-83d8-8cef870ddda3
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 30a03d47-507d-4ad6-83d8-8cef870ddda3
[5 empty] | Drives | Inspect electrical drives overloads settings | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | cc4fe23c-e64f-4960-91b4-de551cb3b347
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | cc4fe23c-e64f-4960-91b4-de551cb3b347
[5 empty] | Gear Box | Inspect gearboxes oil level and color, replace if necessary, VG 220 | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 4d5dbc3b-44b1-4635-b4bc-1a9dfaf8b3da
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 4d5dbc3b-44b1-4635-b4bc-1a9dfaf8b3da
[5 empty] | Belt | Inspect drive belts condition, replace if necessary | planed | 5 | 12 | Annual | Calendar |  |  |  | 5 | 0 | 0 | 0 | 0 | [5 empty] | P06 | ae18b1fc-b779-4cd8-aeed-4fc2bb514cdb
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | ae18b1fc-b779-4cd8-aeed-4fc2bb514cdb
[5 empty] | Electric Connection | Secure and tight all electrical connections and terminals inside control panel | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 5df76c26-b8b7-496d-968e-a473149711c3
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 5df76c26-b8b7-496d-968e-a473149711c3
[5 empty] | Machine Body | Inspect machine body for any damages or cracks | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 7a4f0cb5-c432-4e92-912e-6566c9993192
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 7a4f0cb5-c432-4e92-912e-6566c9993192
[5 empty] | Mechanical Joints | Secure and tight all mechanical joints, screws | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 27e6fc3e-214a-461c-a51d-cf6ad3efe473
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P06 | 27e6fc3e-214a-461c-a51d-cf6ad3efe473
| P07 | Screw Loader | P07 Screw Loader | Marel | Bearing | Grease the bearing | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | e1de6a90-6d79-4224-8423-1227949cce88
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | e1de6a90-6d79-4224-8423-1227949cce88
[5 empty] | Hopper | Check Hopper | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | e5dc0677-e131-4cdf-bc8f-88e325b5e782
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | e5dc0677-e131-4cdf-bc8f-88e325b5e782
[5 empty] | Worm & Shaft | check Worm and mixing shaft | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | c69b412e-cc04-476d-854d-eb0ad3914649
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | c69b412e-cc04-476d-854d-eb0ad3914649
[5 empty] | Gear Box | check oil level in the gearbox. | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 131845f8-410f-41ea-a902-1da34835fe49
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 131845f8-410f-41ea-a902-1da34835fe49
[5 empty] | Bearing | Grease the bearing | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 325ae27a-712b-434a-bfd1-fb7156734120
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 325ae27a-712b-434a-bfd1-fb7156734120
[5 empty] | Bolts | check all bolts | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | b9c27e4a-825b-4c6e-9e40-fc9a84e1b867
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | b9c27e4a-825b-4c6e-9e40-fc9a84e1b867
[5 empty] | Bearing | Check the bearing | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 184eaf4f-6025-4c8d-864b-fced4c34e8c8
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 184eaf4f-6025-4c8d-864b-fced4c34e8c8
[5 empty] | Gear Box | change the gearbox oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 61e23252-4d94-40c9-8c4a-5b4e72ef0af1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 61e23252-4d94-40c9-8c4a-5b4e72ef0af1
[5 empty] | Bearing | Grease the bearing | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 68ff62c0-89e2-468d-94df-22d395433972
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 68ff62c0-89e2-468d-94df-22d395433972
[5 empty] | Hopper | Check Hopper | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 1bad4d27-302b-4cbd-856f-5f4508b89e44
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 1bad4d27-302b-4cbd-856f-5f4508b89e44
[5 empty] | Worm & Shaft | check Worm and mixing shaft | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 5d5003a0-80d5-412a-ac42-c26799403aca
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 5d5003a0-80d5-412a-ac42-c26799403aca
[5 empty] | Gear Box | check oil level in the gearbox. | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | ca96fc0a-e3e0-4188-a941-544b31cbdb34
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | ca96fc0a-e3e0-4188-a941-544b31cbdb34
[5 empty] | Bearing | Grease the bearing | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 0567a05b-bdbf-41e4-b151-633e90dd1a65
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P07 | 0567a05b-bdbf-41e4-b151-633e90dd1a65
| P08 | Minced Mixer | P08 Minced Mixer | Marel | Worm | Inspect the worm and worm head bushing, replace if necessary | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P08 | 6ecba0dc-469e-44da-aea8-0131b7a5add9
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 6ecba0dc-469e-44da-aea8-0131b7a5add9
[5 empty] | Worm | Inspect the worm and worm housing for any damages | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P08 | 07dd28d0-29bf-4d70-8c37-25c94467efd2
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 07dd28d0-29bf-4d70-8c37-25c94467efd2
[5 empty] | Lubrication System | Inpect the operation of automatic lubrication system | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 0965846c-a7ab-40c1-a11c-acff7313c4f1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 0965846c-a7ab-40c1-a11c-acff7313c4f1
[5 empty] | Hydraulic System | Inspect hydraulic system and pump for any leak | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P08 | bd1c7cd8-ced0-45ba-abe7-a97c6a9d52be
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | bd1c7cd8-ced0-45ba-abe7-a97c6a9d52be
[5 empty] | Oil Level | Inspect the oil level of mixers drives gearboxes | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P08 | f63fedf7-1436-4aac-a2d1-3168ce67f1b7
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | f63fedf7-1436-4aac-a2d1-3168ce67f1b7
[5 empty] | Worm | Inspect the worm drive belts, adjust tension if necessary | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P08 | bb4debaa-5c90-4f52-b55c-147e8565a076
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | bb4debaa-5c90-4f52-b55c-147e8565a076
[5 empty] | Housing | Clean the machine housing and wash the seals through the existing water inlets | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 11d43b2d-4adf-405f-8b84-a31497b28ad4
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 11d43b2d-4adf-405f-8b84-a31497b28ad4
[5 empty] | Electric Panel | Clean and isnpect the electrical control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P08 | 494c9f1f-3d56-4b92-b622-a468f30f7d41
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 494c9f1f-3d56-4b92-b622-a468f30f7d41
[5 empty] | Safety Sensors | Test all safety sensors for poper operation | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P08 | 5d46deb8-cf8b-42a4-ba3e-e2cbe97556c1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 5d46deb8-cf8b-42a4-ba3e-e2cbe97556c1
[5 empty] | Precutters & Plates | Inspect precutter (Thickness 19mm) & hole plates (Thickness 19 mm) for any wear or crack, maximum thickness reduction should not be more than 5 mm, make surfacing if necessary | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 5d1fd6e9-45fa-40f4-874f-e727561bad8f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 5d1fd6e9-45fa-40f4-874f-e727561bad8f
[5 empty] | Mixer Shaft | Inspect the mixer shafts and seals | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 3 | 0 | 0 | [5 empty] | P08 | 2d8afe57-3e1d-4794-a1ce-301f3327a2dd
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 2d8afe57-3e1d-4794-a1ce-301f3327a2dd
[5 empty] | Main Cable | Inspect power supply cable and other cables condition | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | b1d11e4a-4a9c-4f2c-badc-a2409e6ddcac
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | b1d11e4a-4a9c-4f2c-badc-a2409e6ddcac
[5 empty] | Electric Connection | Clean and inspect the control panel, tighten and secure electrical connections | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | e59a810a-12bb-43b9-a0df-b101eac3fe2f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | e59a810a-12bb-43b9-a0df-b101eac3fe2f
[5 empty] | Lifter Parts | inspect and lubricate the lifter parts, adjust the chain tension, inspect the drive motor and gearbox, clean the control panel | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 3 | 0 | [5 empty] | P08 | eaaa3c66-d50b-45f0-98e1-894e5f39c423
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | eaaa3c66-d50b-45f0-98e1-894e5f39c423
[5 empty] | Doors | Inspect all doors rubber seal | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 3c0d3b27-0d87-45a5-9164-428e5fb8736c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P08 | 3c0d3b27-0d87-45a5-9164-428e5fb8736c
| P13 | DSI 01 | P13 DSI 01 | Bonner | Rollers | For infeed belt Inspect the carrier rollers, make sure they roll freely | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P13 | 88bd956a-effd-4d87-b00b-7bd217a5b8de
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 88bd956a-effd-4d87-b00b-7bd217a5b8de
[5 empty] | Laser Mounting | Adjust loading laser mounting blocks | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P13 | e8f45a6f-8c81-4e20-ad33-afbc01c04ccc
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | e8f45a6f-8c81-4e20-ad33-afbc01c04ccc
[5 empty] | Laser Strips | Inspect he laser strips, make sure they are straight and aligned | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P13 | d9fc8b55-487e-4c3e-b399-66f3232d3260
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | d9fc8b55-487e-4c3e-b399-66f3232d3260
[5 empty] | Transfer Gaps | For infeed belt,Make sure that transfer gap is 1/8" | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P13 | 5b49c486-610b-459e-8aa4-b0a3a8da9ee3
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 5b49c486-610b-459e-8aa4-b0a3a8da9ee3
[5 empty] | Outfeed Belt | For outfeed belt, inspect spray nozzles, make sure they areon and aligned | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P13 | 967e6d6a-6148-43c8-8dbc-fe0d08c2db10
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 967e6d6a-6148-43c8-8dbc-fe0d08c2db10
[5 empty] | Outfeed Belt | Inspect the condition of outfeed belt, check for any wear | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 7a7c724b-9b11-4ec9-a4d0-2e0770acda5f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 7a7c724b-9b11-4ec9-a4d0-2e0770acda5f
[5 empty] | Bearing | Inspect the the outfeed bearings for any overheat or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P13 | 3e12e7f1-d831-4b86-a304-2645c13a258c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 3e12e7f1-d831-4b86-a304-2645c13a258c
[5 empty] | Sprocket | Inspect the condition of sprockets | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P13 | 5aa8d050-aa95-4119-bcda-4f03b0f08978
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 5aa8d050-aa95-4119-bcda-4f03b0f08978
[5 empty] | Camera Window | Inspect the camera window,clean if necessary | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P13 | 515643e8-445d-42a5-9001-c3da7e310237
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 515643e8-445d-42a5-9001-c3da7e310237
[5 empty] | Laser Alignment | Inspect the scan laser alignment, should be sharp and perpendicular to infeed belt | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 9dc20a44-0f75-46b9-ae4e-3bae05da159e
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P13 | 9dc20a44-0f75-46b9-ae4e-3bae05da159e
| P18 | DSI 02 | P18 DSI 02 | Bonner | Rollers | For infeed belt Inspect the carrier rollers, make sure they roll freely | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P18 | fbe617a5-81e8-4347-818c-bf7d7e12e7e5
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | fbe617a5-81e8-4347-818c-bf7d7e12e7e5
[5 empty] | Laser Mounting | Adjust loading laser mounting blocks | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P18 | 15600686-ebd4-4e60-9b5f-10f88008ecda
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | 15600686-ebd4-4e60-9b5f-10f88008ecda
[5 empty] | Laser Strips | Inspect he laser strips, make sure they are straight and aligned | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P18 | a070b9d5-6912-4290-b831-2e1a96c88042
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | a070b9d5-6912-4290-b831-2e1a96c88042
[5 empty] | Transfer Gaps | For infeed belt,Make sure that transfer gap is 1/8" | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P18 | 17f89382-b4d2-4f59-bd70-cef3fcb6de70
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | 17f89382-b4d2-4f59-bd70-cef3fcb6de70
[5 empty] | Outfeed Belt | For outfeed belt, inspect spray nozzles, make sure they areon and aligned | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P18 | 23e2514d-3ac4-44b1-bdf5-e09d84604d64
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | 23e2514d-3ac4-44b1-bdf5-e09d84604d64
[5 empty] | Outfeed Belt | Inspect the condition of outfeed belt, check for any wear | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P18 | eaaa53af-e722-4e96-8f52-b17284e551cd
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | eaaa53af-e722-4e96-8f52-b17284e551cd
[5 empty] | Bearing | Inspect the the outfeed bearings for any overheat or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P18 | a8da945b-13b8-443d-b305-d870e653d5ca
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | a8da945b-13b8-443d-b305-d870e653d5ca
[5 empty] | Sprocket | Inspect the condition of sprockets | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P18 | a154a732-fcc9-4d84-aa1d-6281420ad0da
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | a154a732-fcc9-4d84-aa1d-6281420ad0da
[5 empty] | Camera Window | Inspect the camera window,clean if necessary | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P18 | 3fbc6e58-887f-4225-92f0-1d74afb95801
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | 3fbc6e58-887f-4225-92f0-1d74afb95801
[5 empty] | Laser Alignment | Inspect the scan laser alignment, should be sharp and perpendicular to infeed belt | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P18 | 45a7b96c-bb30-4766-ac7e-8b0e0631e69b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P18 | 45a7b96c-bb30-4766-ac7e-8b0e0631e69b
| P19 | Tumbler 01 | P19 Tumbler 01 | Bonner | Hydraulic Oil | Inspect the hydraulic oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P19 | 893b2b73-9216-49a1-b8db-c88082aff1f7
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 893b2b73-9216-49a1-b8db-c88082aff1f7
[5 empty] | Vacum | Inspect the oil level for vacuum pump | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 63e4a525-c1d8-4e80-92ef-d24c1b91edd1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 63e4a525-c1d8-4e80-92ef-d24c1b91edd1
[5 empty] | Vacum | Clean the vacuum pump suction filter | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P19 | ce806853-d279-47a4-8dd5-8da2c5b66471
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | ce806853-d279-47a4-8dd5-8da2c5b66471
[5 empty] | Control Panel | Inspect and clean the control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P19 | b4f8aaba-77b7-4fdb-8950-9012a1f9b5b0
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | b4f8aaba-77b7-4fdb-8950-9012a1f9b5b0
[5 empty] | Lids Seal | Inspect the two lids seals | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P19 | 603f2665-59ce-42bb-a9f5-1e6e9f3a91f2
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 603f2665-59ce-42bb-a9f5-1e6e9f3a91f2
[5 empty] | Boiler Banel | inpect and clean the steam generator control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P19 | f91c5fb0-ac31-4267-af38-fad91dbd6d96
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | f91c5fb0-ac31-4267-af38-fad91dbd6d96
[5 empty] | Vaccum Chamber | Inspect the glass vacuum chamber (decanter) and seal for any crack or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P19 | cbb1784e-0eec-4e54-9e13-089707e22c8b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | cbb1784e-0eec-4e54-9e13-089707e22c8b
[5 empty] | Vacum Hoses | Inspect the vacuum hoses and joints for any leak | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 2416a762-cdcd-4fb6-ae30-9ff40e4a7047
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 2416a762-cdcd-4fb6-ae30-9ff40e4a7047
[5 empty] | Drum | Inspect the drum main two drive motros and gearboxes | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 3 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 62b4ea81-a673-46a8-ae34-804586029ba1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 62b4ea81-a673-46a8-ae34-804586029ba1
[5 empty] | Drum | Inspect the drum rotating wheels condition & backside bearing | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 8b4d8b32-6a1b-4fe8-8717-95f8623270ba
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 8b4d8b32-6a1b-4fe8-8717-95f8623270ba
[5 empty] | Lifter Parts | Inspect the lifter drive motor, gearbox and mechanical joints for any damage or loose | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 827b52da-73bc-435e-8837-4c6bc1f9454e
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 827b52da-73bc-435e-8837-4c6bc1f9454e
[5 empty] | Lifter Panel | Inspect and clean the lifter control panel | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 3 | 0 | 0 | 0 | [5 empty] | P19 | 130b639d-9b49-4a64-8832-b61c3d0cc00d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | 130b639d-9b49-4a64-8832-b61c3d0cc00d
[5 empty] | Vacum Pump | Replace the vacuum pump oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 5 | 0 | 0 | 0 | [5 empty] | P19 | c631d3b8-80fd-4aa5-8c6c-3671c93e7f27
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | c631d3b8-80fd-4aa5-8c6c-3671c93e7f27
[5 empty] | Seals | Replace all damaged seals if any | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | d2fe1b79-bd8b-4a0a-9b7e-1f2943216a02
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | d2fe1b79-bd8b-4a0a-9b7e-1f2943216a02
[5 empty] | Drum Motor | Replace drum motors gearboxes oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | f74f2af6-73d6-4204-8124-4008f1ecf30b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P19 | f74f2af6-73d6-4204-8124-4008f1ecf30b
| P20 | Tumbler 02 | P20 Tumbler 02 | Bonner | Hydraulic Oil | Inspect the hydraulic oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P20 | 95b8f77f-e336-42f0-bf55-77981575b901
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 95b8f77f-e336-42f0-bf55-77981575b901
[5 empty] | Vacum | Inspect the oil level for vacuum pump | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P20 | bae76cf9-3396-4550-816c-abe430bac0d3
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | bae76cf9-3396-4550-816c-abe430bac0d3
[5 empty] | Vacum | Clean the vacuum pump suction filter | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 43813892-bc70-408c-bbc3-1dd92575b32b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 43813892-bc70-408c-bbc3-1dd92575b32b
[5 empty] | Control Panel | Inspect and clean the control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P20 | fa4a332d-232b-4348-938c-f99377611831
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | fa4a332d-232b-4348-938c-f99377611831
[5 empty] | Lids Seal | Inspect the two lids seals | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P20 | da2dfbb5-03d0-42bc-9c9f-d92f1ef202ea
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | da2dfbb5-03d0-42bc-9c9f-d92f1ef202ea
[5 empty] | Boiler Banel | inpect and clean the steam generator control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P20 | 8abe780b-ad57-409a-9670-8709d9ee1f94
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 8abe780b-ad57-409a-9670-8709d9ee1f94
[5 empty] | Vaccum Chamber | Inspect the glass vacuum chamber (decanter) and seal for any crack or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 75a3c4dd-f0e1-44f4-8be0-82a4ca246646
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 75a3c4dd-f0e1-44f4-8be0-82a4ca246646
[5 empty] | Vacum Hoses | Inspect the vacuum hoses and joints for any leak | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 5932c987-d31b-42ad-8f86-17c8e4631444
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 5932c987-d31b-42ad-8f86-17c8e4631444
[5 empty] | Drum | Inspect the drum main two drive motros and gearboxes | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | a6b590ef-36a6-439e-81d3-2222274e8440
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | a6b590ef-36a6-439e-81d3-2222274e8440
[5 empty] | Drum | Inspect the drum rotating wheels condition & backside bearing | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 3 | 0 | 0 | [5 empty] | P20 | 33cdf6ae-72de-43e2-9d6a-edeb65e93076
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 33cdf6ae-72de-43e2-9d6a-edeb65e93076
[5 empty] | Lifter Parts | Inspect the lifter drive motor, gearbox and mechanical joints for any damage or loose | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | e6d516d8-01de-4066-8a73-e00648c1e376
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | e6d516d8-01de-4066-8a73-e00648c1e376
[5 empty] | Lifter Panel | Inspect and clean the lifter control panel | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 0d494f54-16a2-431f-9709-6847809dfaf6
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 0d494f54-16a2-431f-9709-6847809dfaf6
[5 empty] | Vacum Pump | Replace the vacuum pump oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 1b7a1193-2482-4b16-875f-1316f8640da3
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 1b7a1193-2482-4b16-875f-1316f8640da3
[5 empty] | Seals | Replace all damaged seals if any | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 1a473015-625c-4249-a98a-9f68f997a31b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | 1a473015-625c-4249-a98a-9f68f997a31b
[5 empty] | Drum Motor | Replace drum motors gearboxes oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | e54e8fe2-d1bf-4e59-9664-a492966f7300
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P20 | e54e8fe2-d1bf-4e59-9664-a492966f7300
| P21 | Tumbler 03 | P21 Tumbler 03 | Bonner | Hydraulic Oil | Inspect the hydraulic oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P21 | 3ec2302d-53f0-468b-a0a7-90eb25203eaf
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 3ec2302d-53f0-468b-a0a7-90eb25203eaf
[5 empty] | Vacum | Inspect the oil level for vacuum pump | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P21 | 052cf185-a449-4474-8927-8630870cc233
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 052cf185-a449-4474-8927-8630870cc233
[5 empty] | Vacum | Clean the vacuum pump suction filter | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P21 | dca49917-c0dc-4a51-879d-c08af2ff1e04
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | dca49917-c0dc-4a51-879d-c08af2ff1e04
[5 empty] | Control Panel | Inspect and clean the control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P21 | ab170344-8407-459d-b26c-7a0ad62d95e5
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | ab170344-8407-459d-b26c-7a0ad62d95e5
[5 empty] | Lids Seal | Inspect the two lids seals | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P21 | bc4ad667-55a3-4f5d-baf4-b164bb6f7027
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | bc4ad667-55a3-4f5d-baf4-b164bb6f7027
[5 empty] | Boiler Banel | inpect and clean the steam generator control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P21 | e8a3495a-c2fb-412b-8160-31da75ee6f6b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | e8a3495a-c2fb-412b-8160-31da75ee6f6b
[5 empty] | Vaccum Chamber | Inspect the glass vacuum chamber (decanter) and seal for any crack or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P21 | 056307d3-e25c-41f3-9cac-c45192ebad13
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 056307d3-e25c-41f3-9cac-c45192ebad13
[5 empty] | Vacum Hoses | Inspect the vacuum hoses and joints for any leak | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 3 | 0 | [5 empty] | P21 | 40f7ca73-7cdf-449c-aafe-fa988546936b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 40f7ca73-7cdf-449c-aafe-fa988546936b
[5 empty] | Drum | Inspect the drum main two drive motros and gearboxes | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | e872bbfc-7e98-406c-87df-79852cd27424
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | e872bbfc-7e98-406c-87df-79852cd27424
[5 empty] | Drum | Inspect the drum rotating wheels condition & backside bearing | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | efe641ee-8769-4e97-8ebe-3d36caa0129c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | efe641ee-8769-4e97-8ebe-3d36caa0129c
[5 empty] | Lifter Parts | Inspect the lifter drive motor, gearbox and mechanical joints for any damage or loose | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 3 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 7276dd87-adbf-4c5b-b14f-65edd5732dcf
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 7276dd87-adbf-4c5b-b14f-65edd5732dcf
[5 empty] | Lifter Panel | Inspect and clean the lifter control panel | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 6aaffe6b-a53e-475a-99fd-6eace83ee272
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 6aaffe6b-a53e-475a-99fd-6eace83ee272
[5 empty] | Vacum Pump | Replace the vacuum pump oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | f25a137a-62b9-44b2-82f7-542b3678515d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | f25a137a-62b9-44b2-82f7-542b3678515d
[5 empty] | Seals | Replace all damaged seals if any | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 290f7e17-4b33-4314-af30-21523ff13bd1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | 290f7e17-4b33-4314-af30-21523ff13bd1
[5 empty] | Drum Motor | Replace drum motors gearboxes oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | e2b92f1f-8552-49cb-a856-c2ff6614fcaf
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P21 | e2b92f1f-8552-49cb-a856-c2ff6614fcaf
| P22 | Tumbler 04 | P22 Tumbler 04 | Bonner | Hydraulic Oil | Inspect the hydraulic oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 4a4893e9-46b0-4631-abeb-840f89c3273d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 4a4893e9-46b0-4631-abeb-840f89c3273d
[5 empty] | Vacum | Inspect the oil level for vacuum pump | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P22 | e888187b-45d7-42fa-9fd8-c01e399990a0
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | e888187b-45d7-42fa-9fd8-c01e399990a0
[5 empty] | Vacum | Clean the vacuum pump suction filter | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P22 | 23263c20-be11-4d7c-952b-63888b6d590e
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 23263c20-be11-4d7c-952b-63888b6d590e
[5 empty] | Control Panel | Inspect and clean the control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P22 | 3f425716-ea2e-4495-b087-7ec80d94c973
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 3f425716-ea2e-4495-b087-7ec80d94c973
[5 empty] | Lids Seal | Inspect the two lids seals | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 3ec6e856-7a62-4b9e-ac79-7821d1e57411
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 3ec6e856-7a62-4b9e-ac79-7821d1e57411
[5 empty] | Boiler Banel | inpect and clean the steam generator control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P22 | dfcf7f34-782f-4a95-b919-7fcd8e340ef0
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | dfcf7f34-782f-4a95-b919-7fcd8e340ef0
[5 empty] | Vaccum Chamber | Inspect the glass vacuum chamber (decanter) and seal for any crack or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P22 | 999da49a-3597-4f23-84d6-4584f4e82843
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 999da49a-3597-4f23-84d6-4584f4e82843
[5 empty] | Vacum Hoses | Inspect the vacuum hoses and joints for any leak | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 1bc28aa0-595b-4749-9de0-40e36fbb9b48
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 1bc28aa0-595b-4749-9de0-40e36fbb9b48
[5 empty] | Drum | Inspect the drum main two drive motros and gearboxes | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 3 | 0 | 0 | 0 | [5 empty] | P22 | 63870450-295a-4261-902d-c431a8d9ea3a
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 63870450-295a-4261-902d-c431a8d9ea3a
[5 empty] | Drum | Inspect the drum rotating wheels condition & backside bearing | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 22ff3793-1603-4947-a569-c08a7f15457d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 22ff3793-1603-4947-a569-c08a7f15457d
[5 empty] | Lifter Parts | Inspect the lifter drive motor, gearbox and mechanical joints for any damage or loose | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | ced674a8-1d0d-4352-9c23-5681e607a2e1
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | ced674a8-1d0d-4352-9c23-5681e607a2e1
[5 empty] | Lifter Panel | Inspect and clean the lifter control panel | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 3 | 0 | 0 | [5 empty] | P22 | 8ec2d711-d3c0-4d55-9210-60dec53a5745
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 8ec2d711-d3c0-4d55-9210-60dec53a5745
[5 empty] | Vacum Pump | Replace the vacuum pump oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 1c6d331a-b1d0-4d4a-9744-a39740f5f4f3
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 1c6d331a-b1d0-4d4a-9744-a39740f5f4f3
[5 empty] | Seals | Replace all damaged seals if any | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 94372f02-241e-4405-af3e-14fba7a9461d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 94372f02-241e-4405-af3e-14fba7a9461d
[5 empty] | Drum Motor | Replace drum motors gearboxes oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 0cd05114-1fe9-4ad2-8b7e-f7742f05ab2b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P22 | 0cd05114-1fe9-4ad2-8b7e-f7742f05ab2b
| P23 | Tumbler 05 | P23 Tumbler 05 | Bonner | Hydraulic Oil | Inspect the hydraulic oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P23 | 0ff6d220-a6ac-4d55-93b2-a79f43deb7dd
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 0ff6d220-a6ac-4d55-93b2-a79f43deb7dd
[5 empty] | Vacum | Inspect the oil level for vacuum pump | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 63396b46-6050-48ab-be6b-04296edbeafe
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 63396b46-6050-48ab-be6b-04296edbeafe
[5 empty] | Vacum | Clean the vacuum pump suction filter | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P23 | 24806d4c-7748-4518-a672-5bdc8e33299c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 24806d4c-7748-4518-a672-5bdc8e33299c
[5 empty] | Control Panel | Inspect and clean the control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P23 | b7ecb018-1e05-43e9-8f02-46b732c896ff
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | b7ecb018-1e05-43e9-8f02-46b732c896ff
[5 empty] | Lids Seal | Inspect the two lids seals | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P23 | 278bc9e9-50d8-4c7f-9114-bde83e3dd6f4
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 278bc9e9-50d8-4c7f-9114-bde83e3dd6f4
[5 empty] | Boiler Banel | inpect and clean the steam generator control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 7041733e-1f46-4cab-b4be-51f4e9f2ee6b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 7041733e-1f46-4cab-b4be-51f4e9f2ee6b
[5 empty] | Vaccum Chamber | Inspect the glass vacuum chamber (decanter) and seal for any crack or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P23 | 15392067-4fda-47bb-9a4d-7fd75b9ebdea
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 15392067-4fda-47bb-9a4d-7fd75b9ebdea
[5 empty] | Vacum Hoses | Inspect the vacuum hoses and joints for any leak | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 08a39fc4-ede3-45ac-bb26-a3cd260e5c61
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 08a39fc4-ede3-45ac-bb26-a3cd260e5c61
[5 empty] | Drum | Inspect the drum main two drive motros and gearboxes | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 6fbe419e-8b8d-483e-a0ff-7ba5156e02b2
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 6fbe419e-8b8d-483e-a0ff-7ba5156e02b2
[5 empty] | Drum | Inspect the drum rotating wheels condition & backside bearing | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 3 | 0 | [5 empty] | P23 | 2ca3050e-1581-48e4-ab8e-593f7b372e31
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 2ca3050e-1581-48e4-ab8e-593f7b372e31
[5 empty] | Lifter Parts | Inspect the lifter drive motor, gearbox and mechanical joints for any damage or loose | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | e5c6ea13-73f1-4767-a9e8-b45d28308953
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | e5c6ea13-73f1-4767-a9e8-b45d28308953
[5 empty] | Lifter Panel | Inspect and clean the lifter control panel | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | b8c51f75-53a5-44c9-8ce8-7a11f2e9b22f
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | b8c51f75-53a5-44c9-8ce8-7a11f2e9b22f
[5 empty] | Vacum Pump | Replace the vacuum pump oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 5 | 0 | 0 | [5 empty] | P23 | 2dacd907-a7dc-46db-9fc7-48bc24b0f1e6
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | 2dacd907-a7dc-46db-9fc7-48bc24b0f1e6
[5 empty] | Seals | Replace all damaged seals if any | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | a45e0f20-8ef3-466f-a3fd-c0d95e4663b8
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | a45e0f20-8ef3-466f-a3fd-c0d95e4663b8
[5 empty] | Drum Motor | Replace drum motors gearboxes oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | e9cdc5ae-fbe1-45ef-8f67-2216f68dd469
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P23 | e9cdc5ae-fbe1-45ef-8f67-2216f68dd469
| P24 | Tumbler 06 | P24 Tumbler 06 | Bonner | Hydraulic Oil | Inspect the hydraulic oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P24 | f63169cb-a8de-4977-9b62-1140b9cc5578
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | f63169cb-a8de-4977-9b62-1140b9cc5578
[5 empty] | Vacum | Inspect the oil level for vacuum pump | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P24 | ac5fd5ee-1672-483b-97fa-18294163a1a8
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | ac5fd5ee-1672-483b-97fa-18294163a1a8
[5 empty] | Vacum | Clean the vacuum pump suction filter | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P24 | db88c1c9-d37b-4bcc-964d-ffd1546647d9
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | db88c1c9-d37b-4bcc-964d-ffd1546647d9
[5 empty] | Control Panel | Inspect and clean the control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P24 | 43607bf4-baa6-48f8-b4f9-ed123e8233bf
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 43607bf4-baa6-48f8-b4f9-ed123e8233bf
[5 empty] | Lids Seal | Inspect the two lids seals | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P24 | 74ce452e-0ba7-4e4d-9cf2-f7237482a6f8
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 74ce452e-0ba7-4e4d-9cf2-f7237482a6f8
[5 empty] | Boiler Banel | inpect and clean the steam generator control panel | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P24 | 28ef5beb-aee3-4759-b069-0bc06908e082
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 28ef5beb-aee3-4759-b069-0bc06908e082
[5 empty] | Vaccum Chamber | Inspect the glass vacuum chamber (decanter) and seal for any crack or damage | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P24 | baf31b71-6ecc-42d4-a419-4c90d054f6e8
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | baf31b71-6ecc-42d4-a419-4c90d054f6e8
[5 empty] | Vacum Hoses | Inspect the vacuum hoses and joints for any leak | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 3 | 0 | 0 | 0 | 0 | [5 empty] | P24 | a73cbc97-9b34-43d2-9d73-3b38242cefdc
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | a73cbc97-9b34-43d2-9d73-3b38242cefdc
[5 empty] | Drum | Inspect the drum main two drive motros and gearboxes | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 74880fca-9e01-4dd5-96c9-bb8e22e7f9b9
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 74880fca-9e01-4dd5-96c9-bb8e22e7f9b9
[5 empty] | Drum | Inspect the drum rotating wheels condition & backside bearing | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | b71707a6-ca8c-4d37-8764-86fe934af062
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | b71707a6-ca8c-4d37-8764-86fe934af062
[5 empty] | Lifter Parts | Inspect the lifter drive motor, gearbox and mechanical joints for any damage or loose | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 3 | 0 | 0 | 0 | [5 empty] | P24 | 92f39799-aa47-41c1-973c-21b74fb0b4ed
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 92f39799-aa47-41c1-973c-21b74fb0b4ed
[5 empty] | Lifter Panel | Inspect and clean the lifter control panel | planed | 3 | 3 | Quarterly | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 00c19e99-85de-44b4-a50a-98aea35a470d
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 00c19e99-85de-44b4-a50a-98aea35a470d
[5 empty] | Vacum Pump | Replace the vacuum pump oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | f569e226-49e6-486c-8113-dfa4df50842a
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | f569e226-49e6-486c-8113-dfa4df50842a
[5 empty] | Seals | Replace all damaged seals if any | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 25788a3b-685d-4750-8b2c-b3134d2f1632
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | 25788a3b-685d-4750-8b2c-b3134d2f1632
[5 empty] | Drum Motor | Replace drum motors gearboxes oil | planed | 5 | 12 | Annual | Calendar |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | bf1396cc-d939-48c9-bdcc-6b06b8f2dafc
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P24 | bf1396cc-d939-48c9-bdcc-6b06b8f2dafc
| P25 | Injector | P25 Injector | GEA | Air Pressure | Inspect the air regulator for needle pneumatic supply, stet to 4 to 6 bar maximum, remove condesate water, check the pneumatic oil level | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P25 | d401860a-c6ea-450d-a5ca-a55ef8d9246c
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | d401860a-c6ea-450d-a5ca-a55ef8d9246c
[5 empty] | Air Pressure | Disconnect the air, open the needle registe, inspect needle register plate, O-Ring, needles condition | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P25 | 81c6c243-ada2-42b7-874d-70753e9dee7b
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | 81c6c243-ada2-42b7-874d-70753e9dee7b
[5 empty] | Holding Plate | Inspect the product holding plate, tight and secure the bolts | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P25 | f7f262d7-5959-47eb-9472-623213d6a344
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | f7f262d7-5959-47eb-9472-623213d6a344
[5 empty] | Transport Plate | Open the Beam walk plate (transport plate), inspect the teflon rollers and bearings | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P25 | db3844f1-e06e-4228-bb1c-6e9cd98ae8db
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | db3844f1-e06e-4228-bb1c-6e9cd98ae8db
[5 empty] | Lifting Rods | Inspect the lifting rods, lifting rods scraper bushings, make sure it is greased | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P25 | ce9f89c3-0bf3-4770-bb9f-008b8d40dec4
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | ce9f89c3-0bf3-4770-bb9f-008b8d40dec4
[5 empty] | Ball Valve | Inspect the brine vlave (ball valve) and its spring | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P25 | e120da23-7794-4c6e-a1e7-29ccfe3ad698
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | e120da23-7794-4c6e-a1e7-29ccfe3ad698
[5 empty] | Main Motor | Inspect the main drive motor and gearbox for any oi leak | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 0 | 2 | 0 | [5 empty] | P25 | 82ad04d1-87ef-49f4-9e60-3ccc7b6d2afe
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | 82ad04d1-87ef-49f4-9e60-3ccc7b6d2afe
[5 empty] | Mechanical Drive | Inspect the main drive cams, arms, rod end bearings and springs, make sure the bearings, cams are lubricated | planed | 2 | 1 | Monthly | Calendar |  |  |  | 2 | 0 | 0 | 0 | 0 | [5 empty] | P25 | cf35409d-0393-4f91-ba98-e932b2904301
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | cf35409d-0393-4f91-ba98-e932b2904301
[5 empty] | Safety Sensor | Activate and test the machine safety sensors and emergency push buttons | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 2 | 0 | 0 | 0 | [5 empty] | P25 | 940d5554-785e-422b-8559-578f3b57cb93
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | 940d5554-785e-422b-8559-578f3b57cb93
[5 empty] | Electric Panel | Inspect and clean electrical control panel, inspect supply cable nad plug | planed | 2 | 1 | Monthly | Calendar |  |  |  | 0 | 0 | 2 | 0 | 0 | [5 empty] | P25 | eee55faf-68f8-408c-b02d-320d06c606dd
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | eee55faf-68f8-408c-b02d-320d06c606dd
[5 empty] | Machine Body | Inspect the condition of machine body, cover for any cracks or damages | planed | 4 | 6 | Semi Annual | Calendar |  |  |  | 0 | 4 | 0 | 0 | 0 | [5 empty] | P25 | 5d1f7ee6-8212-4a4b-83e5-c07cf52a5299
[7 empty] | done | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | P25 | 5d1f7ee6-8212-4a4b-83e5-c07cf52a5299